## Sheet1
Date | Member | Task | Comments
2016-11-02 | Jerry | Concept Creation | RTS Game
2016-11-03 | Jerry | Story Board Writing
2016-11-03 | James | Graphics | Drawing Axeman and Animation
2016-11-03 | Alexei | Graphics | Terrain Development
2016-11-03 | Winston | Story Board Writing
2016-11-03 | Jonathan | Level Design | Plains and River Level
2016-11-09 | Jerry | Story Board Writing
2016-11-09 | James | Graphics
2016-11-09 | Alexei | Graphics
2016-11-16 | Jerry | Game Coding
2016-11-23 | Jerry | Game Coding | Scrapped the Concept because of software complications
2016-11-23 | James | Graphics
2016-11-23 | Alexei | Graphics
2016-11-23 | Jonathan | Level Design
2017-01-04 | Winston | New Concept Creation
2017-01-05 | Winston | Story Board Write
2017-01-05 | James | Graphics
2017-01-05 | Jonathan | Level Design
2017-01-05 | Alexei | Graphics
2017-01-05 | Jerry | Game Coding
2017-01-09 | Winston | Graphics
2017-01-09 | James | Graphics
2017-01-09 | Jonathan | Level Design
2017-01-09 | Alexei | Graphics
2017-01-09 | Jerry | Game Coding
2017-01-23 | Winston | Finding Music
2017-01-23 | James | Graphics
2017-01-23 | Jonathan | Level Design
2017-01-23 | Alexie | Graphics
2017-01-23 | Jerry | Game Coding